## Ballots-Summary_1
WI Responsible body name | WI Responsible body secretariat | WI number | Project ID | Standard nature | Standard reference | Standard title | Launching of ballot | Closing of ballot
CEN/CLC/JTC 21 | DS | JT021019 | 78133 | EN | prEN 18274 | Competence requirements for professional AI ethicists | 2025-09-18 | 2025-12-11
CEN/TC 247 | SNV | 00247139 | 80385 | TR | FprCEN/TR 18276 | Checklist of compliance of building automation with EPBD requirements | 2025-10-02 | 2025-12-25
CEN/CLC/JTC 13 | DIN | JT013089 | 81335 | EN | prEN 40000-1-2 | Cybersecurity requirements for products with digital elements - Part 1-2: Principles for cyber resilience | 2025-10-09 | 2026-01-01
CEN/CLC/JTC 13 | DIN | JT013095 | 82349 | EN | prEN 40000-1-1 | Cybersecurity requirements for products with digital elements - Vocabulary | 2025-10-09 | 2026-01-01
CEN/TC 107 | DS | 00107084 | 73331 | EN | prEN 18213-1 | District heating and district cooling pipes - Bonded single and twin pipe systems for directly buried hot and cold water networks - Part 1: Qualification testing of fitter | 2025-10-09 | 2026-01-01
CEN/TC 107 | DS | 00107086 | 73333 | EN | prEN 18213-2 | District heating and district cooling pipes - Bonded single and twin pipe systems for directly buried hot and cold water networks - Part 2: Qualification testing of PE-Welder | 2025-10-09 | 2026-01-01
CEN/TC 89 | SIS | 00089198 | 72855 | EN | prEN 12667 | Thermal performance of building materials and products - Determination of thermal resistance by means of guarded hot plate and heat flow meter methods - Products of high and medium thermal resistance | 2025-10-16 | 2026-01-08
CEN/TC 89 | SIS | 00089201 | 72858 | EN | prEN 12664 | Thermal performance of building materials and products - Determination of thermal resistance by means of guarded hot plate and heat flow meter methods - Dry and moist products of medium and low thermal resistance | 2025-10-16 | 2026-01-08
CEN/TC 89 | SIS | 00089203 | 72866 | EN | prEN 12939 | Thermal performance of building materials and products - Determination of thermal resistance by means of guarded hot plate and heat flow meter methods - Thick products of high and medium thermal resistance | 2025-10-16 | 2026-01-08
CEN/TC 182 | DIN | 00182101 | 77731 | EN | prEN 14624 | Performance of portable locating leak detectors and of fixed gas detectors for all refrigerants | 2025-11-06 | 2026-01-29
CEN/TC 107 | DS | 00107097 | 81113 | EN | prEN 489-2 | District heating pipes - Factory made flexible pipe systems - Joint casing systems | 2025-11-06 | 2026-01-29
CEN/TC 152 | UNI | 00152022 | 80209 | EN | prEN 13782 | Temporary structure - Tents - Safety | 2025-11-13 | 2026-02-05
CEN/TC 224 | AFNOR | 00224277 | 77618 | TS | FprCEN/TS 18212-1 | Personal identification - Requirements for biometric products - Part 1: General requirements and application profile definition | 2025-11-27 | 2026-02-19
CEN/TC 224 | AFNOR | 00224278 | 77619 | TS | FprCEN/TS 18212-2 | Personal identification - Requirements for biometric products - Part 2: Interoperability tests | 2025-11-27 | 2026-02-19
CEN/CLC/JTC 13 | DIN | JT013090 | 81343 | EN | prEN 40000-1-3 | Cybersecurity requirements for products with digital elements - Part 1-3: Vulnerability Handling | 2025-12-11 | 2026-03-05

## Overview & Work Programme_2
WI Responsible body name | WI Responsible body secretariat | WI number | Project ID | Standard reference | English title | Last realized milestone name | Last realized milestone stagecode | Int rel | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Stage-code | Realization date | Operational plan date | Public comment
CEN/TC 473 | SIS | 00473002 | 80617 | prCEN/TS XXX | Circular Economy - Practical information and guidance for the implementation of ISO 59004:2024 in Europe | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-09-10 | 2024-09-10 | 30.99.0979 |  | 2025-12-15 | [9 empty] | 50.20.0000 |  | 2026-03-16 | 50.60.0000 |  | 2026-06-08 | 60.55.0000 |  | 2026-07-06 | 60.60.0000 |  | 2026-08-03 | OSD
CEN/CLC/JTC 13 | DIN | JT013089 | 81335 | prEN 40000-1-2 | Cybersecurity requirements for products with digital elements - Part 1-2: Principles for cyber resilience | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-03-05 | 2025-03-05 | 30.99.0979 | 2025-09-29 | 2025-09-29 | 40.20.0000 | 2025-10-09 | 2025-10-09 | 40.60.0000 |  | 2026-01-01 | 45.99.0979 |  | 2026-08-27 | 50.20.0000 |  | 2026-11-05 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-02-01 | 60.60.0000 |  | 2027-03-01 | 2025-02-05 : OSD
CEN/CLC/JTC 21 | DS | JT021044 | 80792 | prEN 18288 | Artificial Intelligence - Taxonomy of AI tasks in computer vision | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-11-20 | 2024-11-20 | 30.99.0979 |  | 2026-01-28 | 40.20.0000 |  | 2026-04-29 | 40.60.0000 |  | 2026-07-22 | 45.99.0979 |  | 2026-09-02 | 50.20.0000 |  | 2026-11-12 | 50.60.0000 |  | 2027-01-07 | 60.55.0000 |  | 2027-02-04 | 60.60.0000 |  | 2027-03-04 | OSD
CEN/TC 440 | DIN | 00440028 | 80289 | prEN 17011-5 | Electronic Public Procurement - Architecture - Part 5: Semantic architecture | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-07-03 | 2024-07-03 | 30.99.0979 |  | 2025-11-01 | [9 empty] | 50.20.0000 |  | 2026-02-02 | 50.60.0000 |  | 2026-04-27 | 60.55.0000 |  | 2026-05-25 | 60.60.0000 |  | 2026-06-22 | OSD
CEN/TC 256 | DIN | 00256A4R | 80204 |  | Railway applications - Wheel/Rail Friction Management – Part 3: Rationale for requirements and further background information | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-06-18 | 2024-06-18 | 30.99.0979 |  | 2026-03-17 | [9 empty] | 50.20.0000 |  | 2026-04-21 | 50.60.0000 |  | 2026-07-14 | 60.55.0000 |  | 2026-07-28 | 60.60.0000 |  | 2026-08-11 | OSD
CEN/CLC/JTC 21 | DS | JT021036 | 80353 | prEN 18283 | Artificial Intelligence - Concepts, measures and requirements for managing bias in AI systems | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-08-21 | 2024-08-21 | 30.99.0979 |  | 2026-01-16 | 40.20.0000 |  | 2026-04-17 | 40.60.0000 |  | 2026-07-10 | 45.99.0979 |  | 2027-03-03 | 50.20.0000 |  | 2027-05-12 | 50.60.0000 |  | 2027-07-07 | 60.55.0000 |  | 2027-08-04 | 60.60.0000 |  | 2027-09-01 | OSD
CEN/TC 107 | DS | 00107099 | 81183 | prEN 17248 | District heating and district cooling pipe systems - Terms and definitions | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2025-01-02 | 2025-01-02 | 30.99.0979 | 2025-10-29 | 2025-10-29 | 40.20.0000 |  | 2026-01-15 | 40.60.0000 |  | 2026-04-09 | 45.99.0979 |  | 2026-10-15 | 50.20.0000 |  | 2026-12-24 | 50.60.0000 |  | 2027-02-18 | 60.55.0000 |  | 2027-03-18 | 60.60.0000 |  | 2027-04-15 | 2025-02-26: OSD
CEN/TC 107 | DS | 00107097 | 81113 | prEN 489-2 | District heating pipes - Factory made flexible pipe systems - Joint casing systems | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-12-12 | 2024-12-12 | 30.99.0979 | 2025-07-16 | 2025-07-16 | 40.20.0000 | 2025-11-06 | 2025-11-06 | 40.60.0000 |  | 2026-01-29 | 45.99.0979 |  | 2026-09-24 | 50.20.0000 |  | 2026-12-03 | 50.60.0000 |  | 2027-01-28 | 60.55.0000 |  | 2027-02-25 | 60.60.0000 |  | 2027-03-25 | 2024-12-19 : OSD
CEN/TC 261 | AFNOR | 00261531 | 81842 |  | Packaging — Design for recycling — Part 2: Testing protocol for paper and cardboard packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/TC 261 | AFNOR | 00261548 | 82673 |  | CEN/TS XXXX, Packaging — Design for recycling — Part 1: Process and design criteria to evaluate the recyclability of textile packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-19 | 2025-09-19 | 30.99.0979 |  | 2025-12-28 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 2025-09-24:OSD
CEN/CLC/JTC 24 | DIN | JT024002 | 80081 | prEN 18220 | Digital product passport - Data carriers | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2025-01-29 | 2025-01-29 | 30.99.0979 | 2025-05-14 | 2025-05-14 | 40.20.0000 | 2025-06-26 | 2025-06-26 | 40.60.0000 | 2025-09-18 | 2025-09-18 | 45.99.0979 |  | 2025-11-21 | 50.20.0000 |  | 2026-01-30 | 50.60.0000 |  | 2026-03-27 | 60.55.0000 |  | 2026-04-24 | 60.60.0000 |  | 2026-05-22 | - 2025-05-22 (BdV): Project currently linked to M/604 (not in support of ESPR!) --> impossible to request an assessment. However this is done informally by EC during the daliy collaboratino in drafting the satndards. Waiting for the release of the M/604_AMD that will be linked to the ESPR Regulation 2024/1781 and will allow harmonization (and assessments) under ESPR.WI legislation parameters will be adapted when M/604_AMD is approved. - OSD
CEN/CLC/JTC 21 | DS | JT021019 | 78133 | prEN 18274 | Competence requirements for professional AI ethicists | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-06-19 | 2024-06-19 | 30.99.0979 | 2025-09-10 | 2025-09-10 | 40.20.0000 | 2025-09-18 | 2025-09-18 | 40.60.0000 |  | 2025-12-11 | 45.99.0979 |  | 2027-01-01 | 50.20.0000 |  | 2027-03-12 | 50.60.0000 |  | 2027-05-07 | 60.55.0000 |  | 2027-06-04 | 60.60.0000 |  | 2027-07-02 | OSD 2025-05-22 KG : WI title modified following TC decsiion 10 on 2025-05-15 2024-05-15: WI justification too big & didn't fit in field, last bullet missing: "- the applicability and benefits of implementing the standard across various sectors and contexts"
CEN/TC 224 | AFNOR | 00224278 | 77619 | FprCEN/TS 18212-2 | Personal identification - Requirements for biometric products - Part 2: Interoperability tests | Submission to Vote on TS | 50.20.0000 | Homegrown | 10.99.0000 | 2024-11-13 | 2024-11-13 | 30.99.0979 | 2025-04-24 | 2025-04-24 | [9 empty] | 50.20.0000 | 2025-11-27 | 2025-11-27 | 50.60.0000 |  | 2026-02-19 | 60.55.0000 |  | 2026-03-19 | 60.60.0000 |  | 2026-04-16 | OSD
CEN/TC 460 | DIN | 00460025 | 81361 |  | Food authenticity — Protocol for the collection of honey reference samples for the construction of authenticity databases | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-02-10 | 2025-02-10 | 30.99.0979 |  | 2025-12-15 | 40.20.0000 |  | 2026-03-16 | 40.60.0000 |  | 2026-06-08 | 45.99.0979 |  | 2026-11-23 | 50.20.0000 |  | 2027-02-01 | 50.60.0000 |  | 2027-03-29 | 60.55.0000 |  | 2027-04-26 | 60.60.0000 |  | 2027-05-24 | 2025-02-04: OSD
CEN/TC 250 | BSI | 00250295 | 82038 | prCEN/TS 1995-1-101 | Eurocode 5 - Design of timber structures - Part 1-101: Design assisted by numerical methods | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-05-27 | 2025-05-27 | 30.99.0979 |  | 2026-05-27 | [9 empty] | 50.20.0000 |  | 2026-08-26 | 50.60.0000 |  | 2026-11-18 | 60.55.0000 |  | 2026-12-16 | 60.60.0000 |  | 2027-01-13 | 2025-06-12: OSD
CEN/CLC/JTC 21 | DS | JT021037 | 80364 | prEN 18284 | Artificial Intelligence -- Quality and governance of datasets in AI | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-09-05 | 2024-09-05 | 30.99.0979 |  | 2026-02-01 | 40.20.0000 |  | 2026-05-04 | 40.60.0000 |  | 2026-07-27 | 45.99.0979 |  | 2027-03-18 | 50.20.0000 |  | 2027-05-27 | 50.60.0000 |  | 2027-07-22 | 60.55.0000 |  | 2027-08-19 | 60.60.0000 |  | 2027-09-16 | OSD
CEN/TC 332 | DIN | 00332113 | 82837 | prEN 15154-6 rev | Emergency safety showers - Part 6: Plumbed-in multiple nozzle body showers for sites other than laboratories | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-07 | 2025-10-07 | 30.99.0979 |  | 2026-06-02 | 40.20.0000 |  | 2026-09-01 | 40.60.0000 |  | 2026-11-24 | 45.99.0979 |  | 2027-07-20 | 50.20.0000 |  | 2027-09-28 | 50.60.0000 |  | 2027-11-23 | 60.55.0000 |  | 2027-12-21 | 60.60.0000 |  | 2028-01-18 | 2025-10-13: OSD
CEN/TC 261 | AFNOR | 00261543 | 82000 |  | Packaging — Design for recycling — Part 1: Definitions and general principles of the process and design criteria to evaluate the recyclability of packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-05-16 | 2025-05-16 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 2025-05-20:OSD
CEN/TC 243 | BSI | 00243046 | 82918 | prEN 17141 rev | Cleanrooms and associated controlled environments - Microbiological contamination control | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-27 | 2025-10-27 | 30.99.0979 |  | 2026-06-22 | 40.20.0000 |  | 2026-09-21 | 40.60.0000 |  | 2026-12-14 | 45.99.0979 |  | 2027-08-09 | 50.20.0000 |  | 2027-10-18 | 50.60.0000 |  | 2027-12-13 | 60.55.0000 |  | 2028-01-10 | 60.60.0000 |  | 2028-02-07 | 2025-11-13: OSD
CEN/TC 107 | DS | 00107100 | 81193 |  | District heating and cooling systems — Supplementary information on usage of CEN/TC 107 documents | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-01-08 | 2025-01-08 | 30.99.0979 |  | 2026-01-08 | [9 empty] | 50.20.0000 |  | 2026-02-12 | 50.60.0000 |  | 2026-05-07 | 60.55.0000 |  | 2026-05-21 | 60.60.0000 |  | 2026-06-04 | 2025-01-22:OSD
CEN/TC 467 | UNI | 00467009 | 81435 | prCEN/TR XXX | Adaptation to climate change - Guidelines on using climate data in infrastructure standards | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-02-14 | 2025-02-14 | 30.99.0979 |  | 2026-02-26 | [9 empty] | 50.20.0000 |  | 2026-04-02 | 50.60.0000 |  | 2026-06-25 | 60.55.0000 |  | 2026-07-09 | 60.60.0000 |  | 2026-07-23 | 2025-02-18: OSD
CEN/TC 224 | AFNOR | 00224276 | 77237 | FprCEN/TS 18098 | Guidelines for the onboarding of user personal identification data within European Digital Identity Wallets | Closure of Vote on TS | 50.60.0000 | Homegrown | 10.99.0000 | 2022-12-14 | 2022-12-14 | 30.99.0979 | 2025-04-24 | 2025-04-24 | [9 empty] | 50.20.0000 | 2025-07-17 | 2025-07-17 | 50.60.0000 | 2025-10-09 | 2025-10-09 | 60.55.0000 |  | 2025-11-06 | 60.60.0000 |  | 2025-12-04 | OSD
CEN/CLC/JTC 13 | DIN | JT013091 | 81344 | prEN XXX | Cybersecurity requirements for products with digital elements – Generic Security Requirements | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-03-05 | 2025-03-05 | 30.99.0979 |  | 2025-12-15 | 40.20.0000 |  | 2026-03-16 | 40.60.0000 |  | 2026-06-08 | 45.99.0979 |  | 2026-09-20 | 50.20.0000 |  | 2026-11-30 | 50.60.0000 |  | 2027-01-25 | 60.55.0000 |  | 2027-02-22 | 60.60.0000 |  | 2027-03-22 | OSD: 2025-02-05
CEN/TC 261 | AFNOR | 00261535 | 81847 |  | Packaging — Design for recycling — Part 1: Process and design criteria to evaluate the recyclability of paper and cardboard packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/CLC/JTC 24 | DIN | JT024003 | 80427 | prEN 18216 | Digital product passport - Data exchange protocols | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2025-01-29 | 2025-01-29 | 30.99.0979 | 2025-05-09 | 2025-05-09 | 40.20.0000 | 2025-06-26 | 2025-06-26 | 40.60.0000 | 2025-09-18 | 2025-09-18 | 45.99.0979 |  | 2025-11-21 | 50.20.0000 |  | 2026-01-30 | 50.60.0000 |  | 2026-03-27 | 60.55.0000 |  | 2026-04-24 | 60.60.0000 |  | 2026-05-22 | - 2025-05-22 (BdV): Project currently linked to M/604 (not in support of ESPR!) --> impossible to request an assessment. However this is done informally by EC during the daliy collaboratino in drafting the satndards. Waiting for the release of the M/604_AMD that will be linked to the ESPR Regulation 2024/1781 and will allow harmonization (and assessments) under ESPR.WI legislation parameters will be adapted when M/604_AMD is approved. - OSD
CEN/TC 261 | AFNOR | 00261547 | 82557 | FprCEN/TS XXXX-2 | Packaging - Design for recycling - Part 2: Testing protocol for wood packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-29 | 2025-08-29 | 30.99.0979 |  | 2025-11-03 | [9 empty] | 50.20.0000 |  | 2026-02-02 | 50.60.0000 |  | 2026-04-27 | 60.55.0000 |  | 2026-05-25 | 60.60.0000 |  | 2026-06-22 | 2025-10-13: OSD
CEN/TC 247 | SNV | 00247139 | 80385 | FprCEN/TR 18276 | Checklist of compliance of building automation with EPBD requirements | Submission to Vote on TR | 50.20.0000 | Homegrown | 10.99.0000 | 2024-07-19 | 2024-07-19 | 30.99.0979 | 2025-09-01 | 2025-09-01 | [9 empty] | 50.20.0000 | 2025-10-02 | 2025-10-02 | 50.60.0000 |  | 2025-12-25 | 60.55.0000 |  | 2026-01-08 | 60.60.0000 |  | 2026-01-22 | OSD
CEN/CLC/JTC 22 | DIN | JT022010 | 81991 | prEN XXX | RF & DC lines cabling components for quantum technologies down to ultra-low temperature – Key parameters and test methods | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-16 | 2025-04-16 | 30.99.0979 |  | 2025-12-10 | 40.20.0000 |  | 2026-03-11 | 40.60.0000 |  | 2026-06-03 | 45.99.0979 |  | 2027-01-27 | 50.20.0000 |  | 2027-04-07 | 50.60.0000 |  | 2027-06-02 | 60.55.0000 |  | 2027-06-30 | 60.60.0000 |  | 2027-07-28 | 2025-05-20:OSD
CEN/TC 207 | UNI | 00207320 | 80525 |  | Furniture – Circularity – Guidance on reliability | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-26 | 2025-09-26 | 30.99.0979 |  | 2026-05-22 | 40.20.0000 |  | 2026-08-21 | 40.60.0000 |  | 2026-11-13 | 45.99.0979 |  | 2027-07-09 | 50.20.0000 |  | 2027-09-17 | 50.60.0000 |  | 2027-11-12 | 60.55.0000 |  | 2027-12-10 | 60.60.0000 |  | 2028-01-07 | OSD
CEN/CLC/JTC 13 | DIN | JT013090 | 81343 | prEN 40000-1-3 | Cybersecurity requirements for products with digital elements - Part 1-3: Vulnerability Handling | Acceptance of ENQ draft | 30.99.0979 | Homegrown | 10.99.0000 | 2025-03-05 | 2025-03-05 | 30.99.0979 | 2025-11-27 | 2025-11-27 | 40.20.0000 |  | 2025-12-11 | 40.60.0000 |  | 2026-03-05 | 45.99.0979 |  | 2025-06-06 | 50.20.0000 |  | 2025-08-18 | 50.60.0000 |  | 2025-10-13 | 60.55.0000 |  | 2025-11-10 | 60.60.0000 |  | 2025-12-08 | 2025-02-05 : OSD
CEN/TC 440 | DIN | 00440031 | 82176 | prEN XXX-2-2 | Electronic Public Procurement - Innovation guideline - Part 2-2: Identification of standardization activities to support innovative developments in procurement | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-06-18 | 2025-06-18 | 30.99.0979 |  | 2025-08-18 | [9 empty] | 50.20.0000 |  | 2025-09-22 | 50.60.0000 |  | 2025-12-15 | 60.55.0000 |  | 2026-01-02 | 60.60.0000 |  | 2026-01-16 | 2025-06-26:OSD
CEN/TC 51 | NBN | 00051160 | 76333 | prEN 196-1 rev | Methods of testing cement - Part 1: Determination of strength | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-13 | 2025-11-13 | 30.99.0979 |  | 2026-07-09 | 40.20.0000 |  | 2026-10-08 | 40.60.0000 |  | 2027-01-04 | 45.99.0979 |  | 2027-08-26 | 50.20.0000 |  | 2027-11-04 | 50.60.0000 |  | 2028-01-03 | 60.55.0000 |  | 2028-01-31 | 60.60.0000 |  | 2028-02-28 | OSD
CEN/TC 107 | DS | 00107101 | 81261 | prEN 13941-2 rev | District heating pipes - Design and installation of thermal insulated bonded single and twin pipe systems for directly buried hot water networks - Part 2: Installation | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-01-15 | 2025-01-15 | 30.99.0979 |  | 2026-06-10 | 40.20.0000 |  | 2026-09-09 | 40.60.0000 |  | 2026-12-02 | 45.99.0979 |  | 2027-07-28 | 50.20.0000 |  | 2027-10-06 | 50.60.0000 |  | 2027-12-01 | 60.55.0000 |  | 2028-01-03 | 60.60.0000 |  | 2028-01-31 | 2025-01-22:OSD
CEN/TC 275 | DIN | 00275391 | 81471 | prEN 15634-9 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 9: Fish - Qualitative detection of a specific DNA sequence in food by real-time PCR | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2025-02-20 | 2025-02-20 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 |  | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-12-03 | 50.20.0000 |  | 2027-02-11 | 50.60.0000 |  | 2027-04-08 | 60.55.0000 |  | 2027-05-06 | 60.60.0000 |  | 2027-06-03 | 2025-03-04: OSD
CEN/CLC/JTC 22 | DIN | JT022014 | 82412 | prCEN/CLC/TR XXX | Gaps in IT security evaluation of QKD systems and networks | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-07-24 | 2025-07-24 | 30.99.0979 |  | 2026-09-01 | [9 empty] | 50.20.0000 |  | 2026-10-06 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-01-18 | 60.60.0000 |  | 2027-02-01 | 2025-08-05: OSD
CEN/TC 261 | AFNOR | 00261532 | 81843 |  | Packaging — Design for recycling — Part 2: Evaluation processes for the sortability of packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/TC 152 | UNI | 00152022 | 80209 | prEN 13782 | Temporary structure - Tents - Safety | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-06-17 | 2024-06-17 | 30.99.0979 | 2025-07-24 | 2025-07-24 | 40.20.0000 | 2025-11-13 | 2025-11-13 | 40.60.0000 |  | 2026-02-05 | 45.99.0979 |  | 2026-12-30 | 50.20.0000 |  | 2027-03-10 | 50.60.0000 |  | 2027-05-05 | 60.55.0000 |  | 2027-06-02 | 60.60.0000 |  | 2027-06-30 | 2025-01-17: OSD
CEN/TC 261 | AFNOR | 00261533 | 81845 |  | Packaging — Design for recycling — Part 1: Process and design criteria to evaluate the recyclability of glass packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/CLC/JTC 24 | DIN | JT024006 | 80715 | prEN 18221 | Digital product passport - data storage, archiving, and data persistence | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2025-01-29 | 2025-01-29 | 30.99.0979 | 2025-05-14 | 2025-05-14 | 40.20.0000 | 2025-06-26 | 2025-06-26 | 40.60.0000 | 2025-09-18 | 2025-09-18 | 45.99.0979 |  | 2025-11-21 | 50.20.0000 |  | 2026-01-30 | 50.60.0000 |  | 2026-03-27 | 60.55.0000 |  | 2026-04-24 | 60.60.0000 |  | 2026-05-22 | - 2025-05-22 (BdV): Project currently linked to M/604 (not in support of ESPR!) --> impossible to request an assessment. However this is done informally by EC during the daliy collaboratino in drafting the satndards. Waiting for the release of the M/604_AMD that will be linked to the ESPR Regulation 2024/1781 and will allow harmonization (and assessments) under ESPR.WI legislation parameters will be adapted when M/604_AMD is approved. - OSD
CEN/TC 254 | NEN | 00254200 | 82966 | prEN 13948 rev | Flexible sheets for waterproofing - Bitumen, plastic and rubber sheets for roof waterproofing - Determination of resistance to root penetration | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-04 | 2025-11-04 | 30.99.0979 |  | 2026-06-30 | 40.20.0000 |  | 2026-09-29 | 40.60.0000 |  | 2026-12-22 | 45.99.0979 |  | 2027-08-17 | 50.20.0000 |  | 2027-10-26 | 50.60.0000 |  | 2027-12-21 | 60.55.0000 |  | 2028-01-18 | 60.60.0000 |  | 2028-02-15 | 2025-11-13: OSD
CEN/TC 366 | UNI | 00366023 | 82612 | prCEN/TS 17045 rev | Materials obtained from end-of-life tyres - Quality criteria for the selection of whole tyres, for recovery and recycling processes | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-10 | 2025-09-10 | 30.99.0979 |  | 2026-09-10 | [9 empty] | 50.20.0000 |  | 2026-12-10 | 50.60.0000 |  | 2027-03-04 | 60.55.0000 |  | 2027-04-01 | 60.60.0000 |  | 2027-04-29 | OSD
CEN/TC 162 | DIN | 00162499 | 80770 | prEN 342 rev | Protective clothing - Ensembles and garments for protection against cold | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-10-04 | 2024-10-04 | 30.99.0979 |  | 2025-05-30 | 40.20.0000 |  | 2025-08-29 | 40.60.0000 |  | 2025-11-21 | 45.99.0979 |  | 2026-07-17 | 50.20.0000 |  | 2026-09-25 | 50.60.0000 |  | 2026-11-20 | 60.55.0000 |  | 2026-12-18 | 60.60.0000 |  | 2027-01-15 | 2025-02-18 : OSD
CEN/TC 440 | DIN | 00440025 | 79786 | prEN 17014-2 | Electronic public procurement - Pre-award - Part 2: Transactions | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2024-04-01 | 2024-04-01 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 |  | 2026-01-29 | 40.60.0000 |  | 2026-04-23 | 45.99.0979 |  | 2026-10-12 | 50.20.0000 |  | 2026-12-21 | 50.60.0000 |  | 2027-02-15 | 60.55.0000 |  | 2027-03-15 | 60.60.0000 |  | 2027-04-12 | OSD
CEN/TC 207 | UNI | 00207328 | 81825 |  | Children’s furniture – Tables – Safety requirements and test methods | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-11 | 2025-04-11 | 30.99.0979 |  | 2025-12-05 | 40.20.0000 |  | 2026-03-06 | 40.60.0000 |  | 2026-05-29 | 45.99.0979 |  | 2027-01-22 | 50.20.0000 |  | 2027-04-02 | 50.60.0000 |  | 2027-05-28 | 60.55.0000 |  | 2027-06-25 | 60.60.0000 |  | 2027-07-23 | 2025-04-30:OSD
CEN/TC 224 | AFNOR | 00224282 | 79593 | FprCEN/TS 18297 | EUDI Wallet Held Assets Access Control, Operation and Management | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-08 | 2025-10-08 | 30.99.0979 |  | 2026-10-02 | [9 empty] | 50.20.0000 |  | 2027-01-04 | 50.60.0000 |  | 2027-03-29 | 60.55.0000 |  | 2027-04-26 | 60.60.0000 |  | 2027-05-24 | OSD
CEN/CLC/JTC 22 | DIN | JT022012 | 82296 | prEN XXX | Characterization methods for ion traps used in quantum computing and sensing | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-06-11 | 2025-06-11 | 30.99.0979 |  | 2026-02-04 | 40.20.0000 |  | 2026-05-06 | 40.60.0000 |  | 2026-07-29 | 45.99.0979 |  | 2027-03-24 | 50.20.0000 |  | 2027-06-02 | 50.60.0000 |  | 2027-07-28 | 60.55.0000 |  | 2027-08-25 | 60.60.0000 |  | 2027-09-22 | 2025-07-10:OSD
CEN/TC 128 | NBN | 00128207 | 78535 | prEN 18189 | Rooflights and roof hatches - Environmental Product Declarations - Complementary product category rules (cPCR) to EN 15804 | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-12-15 | 2024-12-15 | 30.99.0979 | 2025-02-17 | 2025-02-17 15:11 | 40.20.0000 | 2025-05-15 | 2025-05-15 | 40.60.0000 | 2025-08-07 | 2025-08-07 | 45.99.0979 |  | 2026-09-27 | 50.20.0000 |  | 2026-12-07 | 50.60.0000 |  | 2027-02-01 | 60.55.0000 |  | 2027-03-01 | 60.60.0000 |  | 2027-03-29 | OSD
CEN/CLC/JTC 21 | DS | JT021008 | 76986 | prEN 18229-1 | AI trustworthiness framework – Part 1: Logging, transparency and human oversight | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-03-20 | 2024-03-20 | 30.99.0979 |  | 2025-08-31 | 40.20.0000 |  | 2025-12-01 | 40.60.0000 |  | 2026-02-23 | 45.99.0979 |  | 2026-11-30 | 50.20.0000 |  | 2027-02-08 | 50.60.0000 |  | 2027-04-05 | 60.55.0000 |  | 2027-05-03 | 60.60.0000 |  | 2027-05-31 | OSD
CEN/TC 248 | BSI | 00248801 | 82127 |  | Smart textiles and electronic textiles — Textile products with active lighting — Determination of the luminance | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-06-06 | 2025-06-06 | 30.99.0979 |  | 2026-04-30 | 40.20.0000 |  | 2026-07-30 | 40.60.0000 |  | 2026-10-22 | 45.99.0979 |  | 2027-03-19 | 50.20.0000 |  | 2027-05-28 | 50.60.0000 |  | 2027-07-23 | 60.55.0000 |  | 2027-08-20 | 60.60.0000 |  | 2027-09-17 | 2025-10-07:OSD
CEN/TC 459/SC 9 | AFNOR | EC109094 | 76270 | prEN 10143 rev | Continuously hot-dip coated steel sheet and strip - Tolerances on dimensions and shape | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-19 | 2025-09-19 | 30.99.0979 |  | 2026-05-15 | 40.20.0000 |  | 2026-08-14 | 40.60.0000 |  | 2026-11-06 | 45.99.0979 |  | 2027-07-02 | 50.20.0000 |  | 2027-09-10 | 50.60.0000 |  | 2027-11-05 | 60.55.0000 |  | 2027-12-03 | 60.60.0000 |  | 2028-01-03 | 2025-03-13: OSD
CEN/TC 143 | SNV | 00143106 | 82167 | prEN 13236 rev | Safety requirements for superabrasive products | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-06-17 | 2025-06-17 | 30.99.0979 |  | 2026-02-10 | 40.20.0000 |  | 2026-05-12 | 40.60.0000 |  | 2026-08-04 | 45.99.0979 |  | 2027-03-30 | 50.20.0000 |  | 2027-06-08 | 50.60.0000 |  | 2027-08-03 | 60.55.0000 |  | 2027-08-31 | 60.60.0000 |  | 2027-09-28 | 2025-06-26:OSD
CEN/TC 182 | DIN | 00182095 | 73150 | prEN 378-1 | Refrigerating systems and heat pumps - Safety and environmental requirements - Part 1: Basic requirements, definitions, classification and selection criteria | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2023-10-27 | 2023-10-27 | 30.99.0979 | 2025-01-31 | 2025-01-31 15:45 | 40.20.0000 | 2025-07-03 | 2025-07-03 | 40.60.0000 | 2025-09-25 | 2025-09-25 | 45.99.0979 |  | 2026-05-08 | 50.20.0000 |  | 2026-07-17 | 50.60.0000 |  | 2026-09-11 | 60.55.0000 |  | 2026-10-09 | 60.60.0000 |  | 2026-11-06 | OSD
CEN/CLC/JTC 22 | DIN | JT022011 | 81992 | prCEN/CLC/TR XXX | Standardization needs for satellite based QKD | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-16 | 2025-04-16 | 30.99.0979 |  | 2026-04-15 | [9 empty] | 50.20.0000 |  | 2026-05-20 | 50.60.0000 |  | 2026-08-12 | 60.55.0000 |  | 2026-08-26 | 60.60.0000 |  | 2026-09-09 | 2025-05-20:OSD
CEN/TC 275 | DIN | 00275390 | 81470 | prEN 15634-8 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 8: Peanut (Arachis hypogaea), hazelnut (Corylus spp.), walnut (Juglans regia) and cashew (Anacardium occidentale) - Qualitative detection of specific DNA sequences in food by real-time PCR | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2025-02-20 | 2025-02-20 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 |  | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-12-03 | 50.20.0000 |  | 2027-02-11 | 50.60.0000 |  | 2027-04-08 | 60.55.0000 |  | 2027-05-06 | 60.60.0000 |  | 2027-06-03 | 2025-03-04: OSD
CEN/CLC/JTC 22 | DIN | JT022015 | 82414 | prCEN/CLC/TR XXX | Design aspects of quantum communication networks | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-07-24 | 2025-07-24 | 30.99.0979 |  | 2026-09-01 | [9 empty] | 50.20.0000 |  | 2026-10-06 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-01-18 | 60.60.0000 |  | 2027-02-01 | 2025-08-05: OSD
CEN/CLC/JTC 21 | DS | JT021025 | 79657 | prEN 18281 | Artificial Intelligence – Evaluation methods for accurate computer vision systems | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-11-20 | 2024-11-20 | 30.99.0979 |  | 2026-03-31 | 40.20.0000 |  | 2026-06-30 | 40.60.0000 |  | 2026-09-22 | 45.99.0979 |  | 2026-09-02 | 50.20.0000 |  | 2026-11-12 | 50.60.0000 |  | 2027-01-07 | 60.55.0000 |  | 2027-02-04 | 60.60.0000 |  | 2027-03-04 | OSD
CEN/TC 264 | DIN | 00264255 | 81988 |  | Stationary source emissions – Diffuse emissions measurement methods – Overview of standards and other documents | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-05-14 | 2025-05-14 | 30.99.0979 |  | 2026-07-31 | [9 empty] | 50.20.0000 |  | 2026-09-04 | 50.60.0000 |  | 2026-11-27 | 60.55.0000 |  | 2026-12-11 | 60.60.0000 |  | 2027-01-04 | 2025-05-27: OSD (Work in OSD is on WI 00264228 despite being abandoned, work will be migrated in OSD in Nov to WI 00262255 before circulation of 1st WD.
CEN/TC 89 | SIS | 00089201 | 72858 | prEN 12664 | Thermal performance of building materials and products - Determination of thermal resistance by means of guarded hot plate and heat flow meter methods - Dry and moist products of medium and low thermal resistance | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-11-14 | 2024-11-14 | 30.99.0979 | 2025-07-08 | 2025-07-08 | 40.20.0000 | 2025-10-16 | 2025-10-16 | 40.60.0000 |  | 2026-01-08 | 45.99.0979 |  | 2026-08-27 | 50.20.0000 |  | 2026-11-05 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-02-01 | 60.60.0000 |  | 2027-03-01 | OSD
CEN/TC 261 | AFNOR | 00261537 | 81849 |  | Packaging — Design for recycling — Part 2: Testing protocol for steel packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 2025-04-28:OSD
CEN/TC 156 | BSI | 00156301 | 79757 | prEN 18289 | Ventilation for buildings - Metallic ventilation ducts - Requirements and test methods | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2024-03-21 | 2024-03-21 | 30.99.0979 | 2025-10-06 | 2025-10-06 | 40.20.0000 |  | 2026-01-29 | 40.60.0000 |  | 2026-04-23 | 45.99.0979 |  | 2026-10-01 | 50.20.0000 |  | 2026-12-10 | 50.60.0000 |  | 2027-02-04 | 60.55.0000 |  | 2027-03-04 | 60.60.0000 |  | 2027-04-01 | 2025-04-07: OSD
CEN/TC 137 | DIN | 00137092 | 76136 |  | Workplace exposure – Measurement of viruses in workplace air | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-01 | 2025-08-01 | 30.99.0979 |  | 2026-05-01 | 40.20.0000 |  | 2026-07-31 | 40.60.0000 |  | 2026-10-23 | 45.99.0979 |  | 2027-01-01 | 50.20.0000 |  | 2027-03-12 | 50.60.0000 |  | 2027-05-07 | 60.55.0000 |  | 2027-06-04 | 60.60.0000 |  | 2027-07-02 | OSD
CEN/TC 247 | SNV | 00247142 | 80862 |  | Uniform method for calculating the CO2 footprint for powered building automation devices | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-10-24 | 2024-10-24 | 30.99.0979 |  | 2026-04-13 | [9 empty] | 50.20.0000 |  | 2026-05-18 | 50.60.0000 |  | 2026-08-10 | 60.55.0000 |  | 2026-08-24 | 60.60.0000 |  | 2026-09-07 | OSD
CEN/TC 469 | AFNOR | 00469004 | 78202 | prEN 18000-3 | Animal health diagnostic analyses - Control of in vitro diagnostic reagents - Part 3: Reagents for PCR techniques | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-06-04 | 2024-06-04 | 30.99.0979 | 2024-12-18 | 2024-12-18 16:26 | 40.20.0000 | 2025-04-03 | 2025-04-03 | 40.60.0000 | 2025-06-26 | 2025-06-26 | 45.99.0979 |  | 2026-05-27 | 50.20.0000 |  | 2026-08-05 | 50.60.0000 |  | 2026-09-30 | 60.55.0000 |  | 2026-10-28 | 60.60.0000 |  | 2026-11-25 | OSD
CEN/TC 175 | AFNOR | 00175197 | 74250 | prEN 16755 | Classes of fire-retardant treated wood products in interior and exterior end use applications - Reaction to fire performance | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-06-24 | 2024-06-24 | 30.99.0979 | 2025-02-04 | 2025-02-04 15:01 | 40.20.0000 | 2025-04-24 | 2025-04-24 | 40.60.0000 | 2025-07-17 | 2025-07-17 | 45.99.0979 |  | 2026-04-06 | 50.20.0000 |  | 2026-06-15 | 50.60.0000 |  | 2026-08-10 | 60.55.0000 |  | 2026-09-07 | 60.60.0000 |  | 2026-10-05 | 2025-10-24: File Attachments (.png) OSD
CEN/TC 98 | DIN | 00098063 | 82714 | prEN 1495 rev | Lifting platforms - Mast climbing work platforms | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-22 | 2025-09-22 | 30.99.0979 |  | 2026-05-18 | 40.20.0000 |  | 2026-08-17 | 40.60.0000 |  | 2026-11-09 | 45.99.0979 |  | 2027-07-05 | 50.20.0000 |  | 2027-09-13 | 50.60.0000 |  | 2027-11-08 | 60.55.0000 |  | 2027-12-06 | 60.60.0000 |  | 2028-01-03 | 2025-09-24: OSD
CEN/CLC/JTC 24 | DIN | JT024004 | 80713 | prEN 18222 | Digital Product Passport - Application Programming Interfaces (APIs) for the product passport lifecycle management and searchability | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2025-01-29 | 2025-01-29 | 30.99.0979 | 2025-05-16 | 2025-05-16 | 40.20.0000 | 2025-06-26 | 2025-06-26 | 40.60.0000 | 2025-09-18 | 2025-09-18 | 45.99.0979 |  | 2025-11-21 | 50.20.0000 |  | 2026-01-30 | 50.60.0000 |  | 2026-03-27 | 60.55.0000 |  | 2026-04-24 | 60.60.0000 |  | 2026-05-22 | - 2025-05-22 (BdV): Project currently linked to M/604 (not in support of ESPR!) --> impossible to request an assessment. However this is done informally by EC during the daliy collaboratino in drafting the satndards. Waiting for the release of the M/604_AMD that will be linked to the ESPR Regulation 2024/1781 and will allow harmonization (and assessments) under ESPR.WI legislation parameters will be adapted when M/604_AMD is approved. - OSD
CEN/TC 440 | DIN | 00440026 | 79792 | prCEN/TS XXX | Electronic Public Procurement - Pre-Award - Part 3-1: Syntax Binding, UBL | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-03-25 | 2024-03-25 | 30.99.0979 |  | 2026-01-01 | [9 empty] | 50.20.0000 |  | 2026-04-02 | 50.60.0000 |  | 2026-06-25 | 60.55.0000 |  | 2026-07-23 | 60.60.0000 |  | 2026-08-20 | OSD
CEN/CLC/JTC 13 | DIN | JT013097 | 82477 |  | Cybersecurity requirements for products with digital elements —Threats and Security Objectives | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-06 | 2025-08-06 | 30.99.0979 |  | 2026-04-01 | 40.20.0000 |  | 2026-07-01 | 40.60.0000 |  | 2026-09-23 | 45.99.0979 |  | 2027-05-19 | 50.20.0000 |  | 2027-07-28 | 50.60.0000 |  | 2027-09-22 | 60.55.0000 |  | 2027-10-20 | 60.60.0000 |  | 2027-11-17 | OSD
CEN/TC 158 | SIS | 00158123 | 82529 | prCEN/TR 16148 rev | Head impact and burn injury criteria - A Guide for CEN helmet standards committees | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-25 | 2025-08-25 | 30.99.0979 |  | 2026-08-18 | [9 empty] | 50.20.0000 |  | 2026-09-22 | 50.60.0000 |  | 2026-12-15 | 60.55.0000 |  | 2027-01-04 | 60.60.0000 |  | 2027-01-18 | 2025-09-12:OSD
CEN/TC 224 | AFNOR | 00224280 | 77621 |  | European requirements for biometric products – Part 5: Face biometrics | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-11-13 | 2024-11-13 | 30.99.0979 |  | 2025-11-13 | [9 empty] | 50.20.0000 |  | 2026-02-12 | 50.60.0000 |  | 2026-05-07 | 60.55.0000 |  | 2026-06-04 | 60.60.0000 |  | 2026-07-02 | OSD
CEN/CLC/JTC 13 | DIN | JT013100 | 82553 | prCEN/CLC/TR XXX | Proof-of-concept for the application of EN 18037 in support of the CRA | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-28 | 2025-08-28 | 30.99.0979 |  | 2026-05-15 | [9 empty] | 50.20.0000 |  | 2026-06-19 | 50.60.0000 |  | 2026-09-11 | 60.55.0000 |  | 2026-09-25 | 60.60.0000 |  | 2026-10-09 | 2025-10-31:OSD
CEN/TC 473 | SIS | 00473004 | 81269 |  | Circular Economy – Extended Producer Responsibility (EPR) – Requirements and guidelines for Producer Responsibility Organizations (PRO) | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-06-05 | 2025-06-05 | 30.99.0979 |  | 2026-01-29 | 40.20.0000 |  | 2026-04-30 | 40.60.0000 |  | 2026-07-23 | 45.99.0979 |  | 2027-03-18 | 50.20.0000 |  | 2027-05-27 | 50.60.0000 |  | 2027-07-22 | 60.55.0000 |  | 2027-08-19 | 60.60.0000 |  | 2027-09-16 | 2025-10-29: OSD until prior to submission to ENQ, project will be converted into VA// CEN lead
CEN/TC 473 | SIS | 00473005 | 81513 |  | Circular economy – Quality classification for remanufacturing processes | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-03-04 | 2025-03-04 | 30.99.0979 |  | 2025-10-28 | 40.20.0000 |  | 2026-01-27 | 40.60.0000 |  | 2026-04-21 | 45.99.0979 |  | 2026-12-15 | 50.20.0000 |  | 2027-02-23 | 50.60.0000 |  | 2027-04-20 | 60.55.0000 |  | 2027-05-18 | 60.60.0000 |  | 2027-06-15 | 2025-03-27: OSD
CEN/TC 256 | DIN | 00256A2A | 75916 | prEN 13749 rev | Railway applications - Wheelsets and bogies - Structural requirements of bogie frames | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-06-16 | 2024-06-16 | 30.99.0979 |  | 2025-11-09 | 40.20.0000 |  | 2026-02-09 | 40.60.0000 |  | 2026-05-04 | 45.99.0979 |  | 2026-12-29 | 50.20.0000 |  | 2027-03-09 | 50.60.0000 |  | 2027-05-04 | 60.55.0000 |  | 2027-06-01 | 60.60.0000 |  | 2027-06-29 | OSD
CEN/TC 260 | DIN | 00260207 | 68251 | prEN 12944-1 | Fertilizers, liming materials and inhibitors - Vocabulary - Part 1: General terms | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2024-10-01 | 2024-10-01 | 30.99.0979 | 2025-10-28 | 2025-10-28 | 40.20.0000 |  | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-07-15 | 50.20.0000 |  | 2026-09-23 | 50.60.0000 |  | 2026-11-18 | 60.55.0000 |  | 2026-12-16 | 60.60.0000 |  | 2027-01-13 | 2025-07-23:OSD
CEN/CLC/JTC 14 | UNI | JT014023 | 78471 | prEN XXX | Values and Benefits of Decarbonisation and Energy Performance Actions - A General Framework for Assessment | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-16 | 2025-04-16 | 30.99.0979 |  | 2026-02-18 | 40.20.0000 |  | 2026-05-20 | 40.60.0000 |  | 2026-08-12 | 45.99.0979 |  | 2027-01-27 | 50.20.0000 |  | 2027-04-07 | 50.60.0000 |  | 2027-06-02 | 60.55.0000 |  | 2027-06-30 | 60.60.0000 |  | 2027-07-28 | 2025-10-31: OSD
CEN/TC 263 | BSI | 00263048 | 82875 |  | Test requirements for fire-protection storage cabinets for lithium-ion batteries in the case of thermal runaway | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-15 | 2025-10-15 | 30.99.0979 |  | 2026-06-10 | 40.20.0000 |  | 2026-09-09 | 40.60.0000 |  | 2026-12-02 | 45.99.0979 |  | 2027-07-28 | 50.20.0000 |  | 2027-10-06 | 50.60.0000 |  | 2027-12-01 | 60.55.0000 |  | 2028-01-03 | 60.60.0000 |  | 2028-01-31 | 2025-11-13: OSD
CEN/TC 261 | AFNOR | 00261549 | 82674 | prCEN/TS XXX | Packaging — Design for recycling — Part 2: Testing protocol for textile packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-18 | 2025-09-18 | 30.99.0979 |  | 2025-12-31 | [9 empty] | 50.20.0000 |  | 2026-04-01 | 50.60.0000 |  | 2026-06-24 | 60.55.0000 |  | 2026-07-22 | 60.60.0000 |  | 2026-08-19 | 2025-09-24:OSD
CEN/CLC/JTC 21 | DS | JT021029 | 79708 | prEN 18282 | Artificial intelligence - Cybersecurity specifications for AI Systems | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-10-02 | 2024-10-02 | 30.99.0979 |  | 2025-08-31 | 40.20.0000 |  | 2025-12-01 | 40.60.0000 |  | 2026-02-23 | 45.99.0979 |  | 2026-07-15 | 50.20.0000 |  | 2026-09-23 | 50.60.0000 |  | 2026-11-18 | 60.55.0000 |  | 2026-12-16 | 60.60.0000 |  | 2027-01-13 | OSD
CEN/CLC/JTC 21 | DS | JT021047 | 82493 | prEN 18229-2 | AI trustworthiness framework – Part 2: Accuracy and robustness | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-05-15 | 2025-05-15 | 30.99.0979 |  | 2026-01-08 | 40.20.0000 |  | 2026-04-09 | 40.60.0000 |  | 2026-07-02 | 45.99.0979 |  | 2027-02-25 | 50.20.0000 |  | 2027-05-06 | 50.60.0000 |  | 2027-07-01 | 60.55.0000 |  | 2027-07-29 | 60.60.0000 |  | 2027-08-26 | OSD
CEN/TC 460 | DIN | 00460023 | 79971 | prEN 18179 | Food authenticity - Method for detecting previously frozen poultry meat by determination of HADH activity | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-04-29 | 2024-04-29 | 30.99.0979 | 2025-01-17 | 2025-01-17 12:14 | 40.20.0000 | 2025-04-17 | 2025-04-17 | 40.60.0000 | 2025-07-10 | 2025-07-10 | 45.99.0979 |  | 2026-02-09 | 50.20.0000 |  | 2026-04-20 | 50.60.0000 |  | 2026-06-15 | 60.55.0000 |  | 2026-07-13 | 60.60.0000 |  | 2026-08-10 | OSD
CEN/TC 107 | DS | 00107102 | 81277 | prEN 13941-1 rev | District heating pipes - Design and installation of thermal insulated bonded single and twin pipe systems for directly buried hot water networks - Part 1: Design | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-01-16 | 2025-01-16 | 30.99.0979 |  | 2026-06-11 | 40.20.0000 |  | 2026-09-10 | 40.60.0000 |  | 2026-12-03 | 45.99.0979 |  | 2027-07-29 | 50.20.0000 |  | 2027-10-07 | 50.60.0000 |  | 2027-12-02 | 60.55.0000 |  | 2028-01-03 | 60.60.0000 |  | 2028-01-31 | 2025-01-22:OSD
CEN/CLC/JTC 13 | DIN | JT013095 | 82349 | prEN 40000-1-1 | Cybersecurity requirements for products with digital elements - Vocabulary | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2025-07-28 | 2025-07-28 | 30.99.0979 | 2025-10-02 | 2025-10-02 | 40.20.0000 | 2025-10-09 | 2025-10-09 | 40.60.0000 |  | 2026-01-01 | 45.99.0979 |  | 2026-06-08 | 50.20.0000 |  | 2026-08-17 | 50.60.0000 |  | 2026-10-12 | 60.55.0000 |  | 2026-11-09 | 60.60.0000 |  | 2026-12-07 | 2025-07-18:OSD
CEN/TC 224 | AFNOR | 00224277 | 77618 | FprCEN/TS 18212-1 | Personal identification - Requirements for biometric products - Part 1: General requirements and application profile definition | Submission to Vote on TS | 50.20.0000 | Homegrown | 10.99.0000 | 2024-11-13 | 2024-11-13 | 30.99.0979 | 2025-04-24 | 2025-04-24 | [9 empty] | 50.20.0000 | 2025-11-27 | 2025-11-27 | 50.60.0000 |  | 2026-02-19 | 60.55.0000 |  | 2026-03-19 | 60.60.0000 |  | 2026-04-16 | OSD
CEN/CLC/JTC 22 | DIN | JT022013 | 82410 | prEN XXX | Entangled Photon-Pair Sources — Characterization requirements and test methods | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-01 | 2025-08-01 | 30.99.0979 |  | 2026-03-27 | 40.20.0000 |  | 2026-06-26 | 40.60.0000 |  | 2026-09-18 | 45.99.0979 |  | 2027-05-14 | 50.20.0000 |  | 2027-07-23 | 50.60.0000 |  | 2027-09-17 | 60.55.0000 |  | 2027-10-15 | 60.60.0000 |  | 2027-11-12 | 2025-08-05: OSD
CEN/TC 224 | AFNOR | 00224287 | 81429 |  | Decomposition of the EUDI Wallet – Part 1: Decomposition of the Solution by Module in the objective of Functional and Security Certifications | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-02-13 | 2025-02-13 | 30.99.0979 |  | 2026-02-02 | [9 empty] | 50.20.0000 |  | 2026-05-04 | 50.60.0000 |  | 2026-07-27 | 60.55.0000 |  | 2026-08-24 | 60.60.0000 |  | 2026-09-21 | 2025-02-18: OSD
CEN/TC 275 | DIN | 00275385 | 80389 |  | Foodstuffs - Determination of elements and their chemical species - Determination of methylmercury in foodstuffs by HPLC-ICP-MS | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-14 | 2025-08-14 | 30.99.0979 |  | 2026-04-09 | 40.20.0000 |  | 2026-07-09 | 40.60.0000 |  | 2026-10-01 | 45.99.0979 |  | 2027-05-27 | 50.20.0000 |  | 2027-08-05 | 50.60.0000 |  | 2027-09-30 | 60.55.0000 |  | 2027-10-28 | 60.60.0000 |  | 2027-11-25 | OSD
CEN/TC 459/SC 9 | AFNOR | EC109095 | 76271 | prEN 10131 rev | Cold rolled uncoated and zinc or zinc-nickel electrolytically coated low carbon and high yield strength steel flat products for cold forming - Tolerances on dimensions and shape | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-19 | 2025-09-19 | 30.99.0979 |  | 2026-05-15 | 40.20.0000 |  | 2026-08-14 | 40.60.0000 |  | 2026-11-06 | 45.99.0979 |  | 2027-07-02 | 50.20.0000 |  | 2027-09-10 | 50.60.0000 |  | 2027-11-05 | 60.55.0000 |  | 2027-12-03 | 60.60.0000 |  | 2028-01-03 | 2025-03-13: OSD
CEN/TC 182 | DIN | 00182094 | 73149 | prEN 378-5 | Refrigerating systems and heat pumps - Safety and environmental requirements - Part 5: Safety classification and information about refrigerants | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2023-10-27 | 2023-10-27 | 30.99.0979 | 2025-01-31 | 2025-01-31 15:48 | 40.20.0000 | 2025-07-03 | 2025-07-03 | 40.60.0000 | 2025-09-25 | 2025-09-25 | 45.99.0979 |  | 2026-05-08 | 50.20.0000 |  | 2026-07-17 | 50.60.0000 |  | 2026-09-11 | 60.55.0000 |  | 2026-10-09 | 60.60.0000 |  | 2026-11-06 | OSD
CEN/TC 460 | DIN | 00460031 | 82984 |  | Food authenticity — Quantification of adulterant plant material in paprika/chilli, saffron, cumin, turmeric, oregano and black pepper by quantitative PCR | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-10 | 2025-11-10 | 30.99.0979 |  | 2027-01-01 | [9 empty] | 50.20.0000 |  | 2027-04-02 | 50.60.0000 |  | 2027-06-25 | 60.55.0000 |  | 2027-07-23 | 60.60.0000 |  | 2027-08-20 | 2025-11-24: OSD
CEN/TC 247 | SNV | 00247144 | 81313 |  | Proactive buildings - Integrating adaptive design and intelligent operations | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-01-21 | 2025-01-21 | 30.99.0979 |  | 2026-01-21 | [9 empty] | 50.20.0000 |  | 2026-02-25 | 50.60.0000 |  | 2026-05-20 | 60.55.0000 |  | 2026-06-03 | 60.60.0000 |  | 2026-06-17 | 2025-02-04: OSD
CEN/TC 447 | BSI | 00447005 | 76806 | prEN 18306 | Provision of services - Guidance for organizations which provide lists of prequalified, qualified or shortlisted service providers | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2025-10-06 | 2025-10-06 | 30.99.0979 | 2025-11-13 | 2025-11-13 | 40.20.0000 |  | 2026-01-29 | 40.60.0000 |  | 2026-04-23 | 45.99.0979 |  | 2027-03-30 | 50.20.0000 |  | 2027-06-08 | 50.60.0000 |  | 2027-08-03 | 60.55.0000 |  | 2027-08-31 | 60.60.0000 |  | 2027-09-28 | 2024-01-06: OSD
CEN/TC 107 | DS | 00107086 | 73333 | prEN 18213-2 | District heating and district cooling pipes - Bonded single and twin pipe systems for directly buried hot and cold water networks - Part 2: Qualification testing of PE-Welder | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-08-12 | 2024-08-12 | 30.99.0979 | 2025-04-24 | 2025-04-24 | 40.20.0000 | 2025-10-09 | 2025-10-09 | 40.60.0000 |  | 2026-01-01 | 45.99.0979 |  | 2026-05-25 | 50.20.0000 |  | 2026-08-03 | 50.60.0000 |  | 2026-09-28 | 60.55.0000 |  | 2026-10-26 | 60.60.0000 |  | 2026-11-23
CEN/TC 278 | NEN | 00278647 | 80574 | prEN 16986 rev | Electronic fee collection - Interoperable application profiles for information exchange between service provision and toll charging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-08-26 | 2024-08-26 | 30.99.0979 |  | 2025-04-21 | 40.20.0000 |  | 2025-07-22 | 40.60.0000 |  | 2025-10-14 | 45.99.0979 |  | 2026-06-08 | 50.20.0000 |  | 2026-08-17 | 50.60.0000 |  | 2026-10-12 | 60.55.0000 |  | 2026-11-09 | 60.60.0000 |  | 2026-12-07 | 20251125_IC: EN 16986 Significant progress is made in the preparation of EN 16986. The draft is very close to submission to CEN Enquiry. The main changes are as follows: -updated data definitions to reflect changes made to the underlying base standard EN ISO 12855:2025, including its enhanced support for ANPR-based fee collection -updated interoperability application profiles tailored according to electronic fee collection (EFC) charging policies and primary used technologies; -updated terms and definitions, including reference to EN ISO 17573-2 as the primary source As mentioned above, it is quite likely that technical comments will be received during the Enquiry phase which will call for an updated version to be submitted to the FV. EN 16986 (ed. 2) is expected to be adopted by CEN by 31 March 2027.
CEN/CLC/JTC 24 | DIN | JT024001 | 79954 | prEN 18219 | Digital product passport - Unique identifiers | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2025-01-29 | 2025-01-29 | 30.99.0979 | 2025-05-14 | 2025-05-14 | 40.20.0000 | 2025-06-26 | 2025-06-26 | 40.60.0000 | 2025-09-18 | 2025-09-18 | 45.99.0979 |  | 2025-11-21 | 50.20.0000 |  | 2026-01-30 | 50.60.0000 |  | 2026-03-27 | 60.55.0000 |  | 2026-04-24 | 60.60.0000 |  | 2026-05-22 | - 2025-05-22 (BdV): Project currently linked to M/604 (not in support of ESPR!) --> impossible to request an assessment. However this is done informally by EC during the daliy collaboratino in drafting the satndards. Waiting for the release of the M/604_AMD that will be linked to the ESPR Regulation 2024/1781 and will allow harmonization (and assessments) under ESPR.WI legislation parameters will be adapted when M/604_AMD is approved. - OSD
CEN/TC 261 | AFNOR | 00261536 | 81848 |  | Packaging — Design for recycling — Part 1: Process and design criteria to evaluate the recyclability of steel packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 2025-04-28:OSD
CEN/CLC/JTC 13 | DIN | JT013099 | 82552 | prCEN/CLC/TS XXX | Guidance for the application of EN 18037 in support of the CRA | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-28 | 2025-08-28 | 30.99.0979 |  | 2026-05-15 | [9 empty] | 50.20.0000 |  | 2026-08-14 | 50.60.0000 |  | 2026-11-06 | 60.55.0000 |  | 2026-12-04 | 60.60.0000 |  | 2027-01-04 | 2025-10-31:OSD
CEN/TC 169 | DIN | 00169098 | 76697 | prEN 17037 rev | Daylight in buildings | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-19 | 2025-09-19 | 30.99.0979 |  | 2026-11-27 | 40.20.0000 |  | 2027-02-26 | 40.60.0000 |  | 2027-05-21 | 45.99.0979 |  | 2027-07-02 | 50.20.0000 |  | 2027-09-10 | 50.60.0000 |  | 2027-11-05 | 60.55.0000 |  | 2027-12-03 | 60.60.0000 |  | 2028-01-03 | 2025-02-13: OSD
CEN/TC 207 | UNI | 00207321 | 80526 |  | Furniture — Circularity — Evaluation method for maintenance, repair and refurbishing capability | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-26 | 2025-09-26 | 30.99.0979 |  | 2026-05-22 | 40.20.0000 |  | 2026-08-21 | 40.60.0000 |  | 2026-11-13 | 45.99.0979 |  | 2027-07-09 | 50.20.0000 |  | 2027-09-17 | 50.60.0000 |  | 2027-11-12 | 60.55.0000 |  | 2027-12-10 | 60.60.0000 |  | 2028-01-07 | OSD
CEN/TC 440 | DIN | 00440029 | 82174 | prEN XXX-2-3 | Electronic Public Procurement - Innovation guideline - Part 2-3: Legislation and regulations to enable and support innovative developments in procurement | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-06-18 | 2025-06-18 | 30.99.0979 |  | 2025-08-18 | [9 empty] | 50.20.0000 |  | 2025-09-22 | 50.60.0000 |  | 2025-12-15 | 60.55.0000 |  | 2026-01-02 | 60.60.0000 |  | 2026-01-16 | 2025-06-26:OSD
CEN/TC 260 | DIN | 00260208 | 68254 | prEN 12944-2 | Fertilizers, liming materials and inhibitors - Vocabulary - Part 2: Terms relating to fertilizers | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2024-10-01 | 2024-10-01 | 30.99.0979 | 2025-10-28 | 2025-10-28 | 40.20.0000 |  | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-07-15 | 50.20.0000 |  | 2026-09-23 | 50.60.0000 |  | 2026-11-18 | 60.55.0000 |  | 2026-12-16 | 60.60.0000 |  | 2027-01-13 | 2025-07-23:OSD
CEN/TC 275 | DIN | 00275388 | 81468 | prEN 15634-6 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 6: Wheat (Triticum L.) and Rye (Secale cereale) - Qualitative detection of a specific DNA sequence in cooked sausages by real-time PCR | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2025-02-20 | 2025-02-20 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 |  | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-12-03 | 50.20.0000 |  | 2027-02-11 | 50.60.0000 |  | 2027-04-08 | 60.55.0000 |  | 2027-05-06 | 60.60.0000 |  | 2027-06-03 | 2025-03-04: OSD
CEN/TC 19 | NEN | 00019688 | 82877 | prEN 16423 rev | Liquefied petroleum gases - Determination of dissolved residue - Gas chromatographic method using liquid, on-column injection | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-16 | 2025-10-16 | 30.99.0979 |  | 2026-06-11 | 40.20.0000 |  | 2026-09-10 | 40.60.0000 |  | 2026-12-03 | 45.99.0979 |  | 2027-07-29 | 50.20.0000 |  | 2027-10-07 | 50.60.0000 |  | 2027-12-02 | 60.55.0000 |  | 2028-01-03 | 60.60.0000 |  | 2028-01-31 | 2025-11-13: OSD
CEN/TC 256 | DIN | 00256A5M | 82307 | prEN 16891 rev | EN 16891, Railway applications - Acoustics - Measurement method for combined roughness, track decay rates and transfer functions | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-07-11 | 2025-07-11 | 30.99.0979 |  | 2026-03-06 | 40.20.0000 |  | 2026-06-05 | 40.60.0000 |  | 2026-08-28 | 45.99.0979 |  | 2027-04-23 | 50.20.0000 |  | 2027-07-02 | 50.60.0000 |  | 2027-08-27 | 60.55.0000 |  | 2027-09-24 | 60.60.0000 |  | 2027-10-22 | 2025-07-17:OSD
CEN/TC 261 | AFNOR | 00261546 | 82556 | FprCEN/TS XXXX-1 | Packaging - Design for recycling - Part 1: Process and design criteria to evaluate the recyclability of wood packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-29 | 2025-08-29 | 30.99.0979 |  | 2026-11-01 | [9 empty] | 50.20.0000 |  | 2027-02-01 | 50.60.0000 |  | 2027-04-26 | 60.55.0000 |  | 2027-05-24 | 60.60.0000 |  | 2027-06-21 | 2025-09-24: OSD document
CEN/TC 473 | SIS | 00473001 | 80616 | prCEN/TS XXX | Circular economy - Guidance on the implementation of ISO 59010 with consideration of European policies and regulations | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2024-09-10 | 2024-09-10 | 30.99.0979 |  | 2026-06-09 | [9 empty] | 50.20.0000 |  | 2026-09-08 | 50.60.0000 |  | 2026-12-01 | 60.55.0000 |  | 2027-01-04 | 60.60.0000 |  | 2027-02-01 | OSD
CEN/TC 264 | DIN | 00264233 | 76800 | prEN XXX | Ambient air quality - Diffusive samplers for the determination of concentrations of gases - Requirements, validation methods and use | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-07-02 | 2025-07-02 | 30.99.0979 |  | 2026-04-30 | 40.20.0000 |  | 2026-07-30 | 40.60.0000 |  | 2026-10-22 | 45.99.0979 |  | 2027-04-14 | 50.20.0000 |  | 2027-06-23 | 50.60.0000 |  | 2027-08-18 | 60.55.0000 |  | 2027-09-15 | 60.60.0000 |  | 2027-10-13 | 2025-07-09: OSD
CEN/TC 440 | DIN | 00440030 | 82175 | prEN XXX-2-1 | Electronic Public Procurement - Innovation guideline - Part 2-1: Framework and models of innovative developments in procurement | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-06-18 | 2025-06-18 | 30.99.0979 |  | 2025-08-18 | [9 empty] | 50.20.0000 |  | 2025-09-22 | 50.60.0000 |  | 2025-12-15 | 60.55.0000 |  | 2026-01-02 | 60.60.0000 |  | 2026-01-16 | 2025-06-26:OSD
CEN/TC 261 | AFNOR | 00261538 | 81850 |  | Packaging — Design for recycling — Part 2: Testing protocol for glass packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/TC 182 | DIN | 00182096 | 73151 | prEN 378-3 | Refrigerating systems and heat pumps - Safety and environmental requirements - Part 3: Installation site and personal protection | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2023-10-27 | 2023-10-27 | 30.99.0979 | 2025-01-31 | 2025-01-31 15:47 | 40.20.0000 | 2025-07-03 | 2025-07-03 | 40.60.0000 | 2025-09-25 | 2025-09-25 | 45.99.0979 |  | 2026-05-08 | 50.20.0000 |  | 2026-07-17 | 50.60.0000 |  | 2026-09-11 | 60.55.0000 |  | 2026-10-09 | 60.60.0000 |  | 2026-11-06 | OSD
CEN/TC 256 | DIN | 00256A1Q | 74943 | prCEN/TR 14363-6 | Railway applications - Testing and simulation for the assessment of running characteristics of railway vehicles operated on the heavy rail network - Part 6: Technical Report providing background information to the EN 14363 series of standards | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2024-09-13 | 2024-09-13 | 30.99.0979 |  | 2026-06-14 | [9 empty] | 50.20.0000 |  | 2026-07-20 | 50.60.0000 |  | 2026-10-12 | 60.55.0000 |  | 2026-10-26 | 60.60.0000 |  | 2026-11-09 | 2025-03-17: OSD
CEN/TC 350 | AFNOR | 00350039 | 75207 | prEN 18177 | Circular economy in the construction sector - Framework, principles, and definitions | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2024-05-02 | 2024-05-02 | 30.99.0979 | 2025-01-16 | 2025-01-16 09:11 | 40.20.0000 | 2025-04-10 | 2025-04-10 | 40.60.0000 | 2025-07-03 | 2025-07-03 | 45.99.0979 |  | 2026-02-12 | 50.20.0000 |  | 2026-04-23 | 50.60.0000 |  | 2026-06-18 | 60.55.0000 |  | 2026-07-16 | 60.60.0000 |  | 2026-08-13 | OSD
CEN/TC 256 | DIN | 00256A2O | 76296 | prEN 17833 rev | Railway applications - Simulation Credibility | Circulation of 1st WD | 20.60.0979 | Homegrown | 10.99.0000 | 2025-06-25 | 2025-06-25 | 30.99.0979 |  | 2026-02-18 | 40.20.0000 |  | 2026-05-20 | 40.60.0000 |  | 2026-08-12 | 45.99.0979 |  | 2027-04-07 | 50.20.0000 |  | 2027-06-16 | 50.60.0000 |  | 2027-08-11 | 60.55.0000 |  | 2027-09-08 | 60.60.0000 |  | 2027-10-06 | OSD
CEN/TC 354 | AFNOR | 00354010 | 80375 | prEN 16230-1 rev | Leisure karts - Part 1: Safety requirements and test methods for karts | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2023-12-20 | 2023-12-20 | 30.99.0979 |  | 2025-11-02 | 40.20.0000 |  | 2026-02-02 | 40.60.0000 |  | 2026-04-27 | 45.99.0979 |  | 2026-06-02 | 50.20.0000 |  | 2026-08-11 | 50.60.0000 |  | 2026-10-06 | 60.55.0000 |  | 2026-11-03 | 60.60.0000 |  | 2026-12-01 | OSD
CEN/TC 247 | SNV | 00247137 | 79075 | EN 17691-1:2025 | Components for BAC control loops - Valve and actuator assemblies - Part 1: Water-based HVAC applications | DOR/Ratification | 60.55.0000 | Homegrown | 10.99.0000 | 2023-11-20 | 2023-11-20 | 30.99.0979 | 2024-07-22 | 2024-07-22 | 40.20.0000 | 2024-10-17 | 2024-10-17 | 40.60.0000 | 2025-01-09 | 2025-01-09 | 45.99.0979 | 2025-06-23 | 2025-06-23 | 50.20.0000 | 2025-08-14 | 2025-08-14 | 50.60.0000 | 2025-10-09 | 2025-10-09 | 60.55.0000 | 2025-11-10 | 2025-11-10 | 60.60.0000 |  | 2025-12-17 | OSD commenting pilot
CEN/TC 477 | SIS | 00477001 | 83050 |  | Information on mineral and metal raw materials processing schemes with consideration to European policies and regulations | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-21 | 2025-11-21 | 30.99.0979 |  | 2026-09-11 | [9 empty] | 50.20.0000 |  | 2026-10-16 | 50.60.0000 |  | 2027-01-08 | 60.55.0000 |  | 2027-01-22 | 60.60.0000 |  | 2027-02-05 | 2025-11-24: OSD
CEN/TC 224 | AFNOR | 00224288 | 81586 |  | Personal identification — European requirements for biometric products — Part 4: Fingerprint biometrics | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-11-20 | 2025-11-20 | 30.99.0979 |  | 2026-11-18 | [9 empty] | 50.20.0000 |  | 2027-02-17 | 50.60.0000 |  | 2027-05-12 | 60.55.0000 |  | 2027-06-09 | 60.60.0000 |  | 2027-07-07 | 2025-04-02: OSD
CEN/TC 107 | DS | 00107084 | 73331 | prEN 18213-1 | District heating and district cooling pipes - Bonded single and twin pipe systems for directly buried hot and cold water networks - Part 1: Qualification testing of fitter | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-08-12 | 2024-08-12 | 30.99.0979 | 2025-04-24 | 2025-04-24 | 40.20.0000 | 2025-10-09 | 2025-10-09 | 40.60.0000 |  | 2026-01-01 | 45.99.0979 |  | 2026-05-25 | 50.20.0000 |  | 2026-08-03 | 50.60.0000 |  | 2026-09-28 | 60.55.0000 |  | 2026-10-26 | 60.60.0000 |  | 2026-11-23
CEN/TC 440 | DIN | 00440024 | 79785 | prEN 17014-1 | Electronic public procurement - Pre-award - Part 1: Choreographies | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2024-04-01 | 2024-04-01 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 |  | 2026-01-29 | 40.60.0000 |  | 2026-04-23 | 45.99.0979 |  | 2026-10-12 | 50.20.0000 |  | 2026-12-21 | 50.60.0000 |  | 2027-02-15 | 60.55.0000 |  | 2027-03-15 | 60.60.0000 |  | 2027-04-12 | OSD
CEN/CLC/JTC 24 | DIN | JT024005 | 80714 | prEN 18223 | Digital Product Passport - System interoperability | Closure of Enquiry | 40.60.0000 | Homegrown | 10.99.0000 | 2025-01-29 | 2025-01-29 | 30.99.0979 | 2025-05-16 | 2025-05-16 | 40.20.0000 | 2025-06-26 | 2025-06-26 | 40.60.0000 | 2025-09-18 | 2025-09-18 | 45.99.0979 |  | 2025-11-21 | 50.20.0000 |  | 2026-01-30 | 50.60.0000 |  | 2026-03-27 | 60.55.0000 |  | 2026-04-24 | 60.60.0000 |  | 2026-05-22 | - 2025-05-22 (BdV): Project currently linked to M/604 (not in support of ESPR!) --> impossible to request an assessment. However this is done informally by EC during the daliy collaboratino in drafting the satndards. Waiting for the release of the M/604_AMD that will be linked to the ESPR Regulation 2024/1781 and will allow harmonization (and assessments) under ESPR.WI legislation parameters will be adapted when M/604_AMD is approved. - OSD
CEN/TC 155 | NEN | 00155A2H | 82112 | prCEN/TS 14758-2 rev | Plastics piping systems for non‐pressure underground drainage and sewerage - Polypropylene with mineral modifiers (PP‐MD) - Part 2: Assessment of conformity | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-06-04 | 2025-06-04 | 30.99.0979 |  | 2026-06-04 | [9 empty] | 50.20.0000 |  | 2026-09-03 | 50.60.0000 |  | 2026-11-26 | 60.55.0000 |  | 2026-12-24 | 60.60.0000 |  | 2027-01-21 | 2025-06-12: OSD
CEN/TC 89 | SIS | 00089198 | 72855 | prEN 12667 | Thermal performance of building materials and products - Determination of thermal resistance by means of guarded hot plate and heat flow meter methods - Products of high and medium thermal resistance | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-11-17 | 2024-11-17 | 30.99.0979 | 2025-07-08 | 2025-07-08 | 40.20.0000 | 2025-10-16 | 2025-10-16 | 40.60.0000 |  | 2026-01-08 | 45.99.0979 |  | 2026-08-30 | 50.20.0000 |  | 2026-11-09 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-02-01 | 60.60.0000 |  | 2027-03-01 | OSD
CEN/TC 224 | AFNOR | 00224286 | 81428 |  | Decomposition of the EUDI Wallet – Part 2: Decomposition of the Provider by Service in the objective of Functional and Security Certifications | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-02-13 | 2025-02-13 | 30.99.0979 |  | 2026-02-02 | [9 empty] | 50.20.0000 |  | 2026-05-04 | 50.60.0000 |  | 2026-07-27 | 60.55.0000 |  | 2026-08-24 | 60.60.0000 |  | 2026-09-21 | 2025-02-18: OSD
CEN/TC 194 | AFNOR | 00194170 | 80131 |  | Evaluation of the suitability of metal and alloy articles in contact with foodstuffs during microwave heating | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-01-22 | 2025-01-22 | 30.99.0979 |  | 2025-09-17 | 40.20.0000 |  | 2025-12-17 | 40.60.0000 |  | 2026-03-11 | 45.99.0979 |  | 2026-11-04 | 50.20.0000 |  | 2027-01-13 | 50.60.0000 |  | 2027-03-10 | 60.55.0000 |  | 2027-04-07 | 60.60.0000 |  | 2027-05-05 | 2025-02-05: OSD
CEN/TC 89 | SIS | 00089203 | 72866 | prEN 12939 | Thermal performance of building materials and products - Determination of thermal resistance by means of guarded hot plate and heat flow meter methods - Thick products of high and medium thermal resistance | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-11-17 | 2024-11-17 | 30.99.0979 | 2025-07-08 | 2025-07-08 | 40.20.0000 | 2025-10-16 | 2025-10-16 | 40.60.0000 |  | 2026-01-08 | 45.99.0979 |  | 2026-08-30 | 50.20.0000 |  | 2026-11-09 | 50.60.0000 |  | 2027-01-04 | 60.55.0000 |  | 2027-02-01 | 60.60.0000 |  | 2027-03-01 | OSD
CEN/CLC/JTC 21 | DS | JT021035 | 80227 | prEN 18287 | Sustainable Artificial Intelligence – Guidelines and metrics for the environmental impact of artificial intelligence systems and services | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-09-30 | 2025-09-30 | 30.99.0979 |  | 2026-05-26 | 40.20.0000 |  | 2026-08-25 | 40.60.0000 |  | 2026-11-17 | 45.99.0979 |  | 2027-07-13 | 50.20.0000 |  | 2027-09-21 | 50.60.0000 |  | 2027-11-16 | 60.55.0000 |  | 2027-12-14 | 60.60.0000 |  | 2028-01-11 | 2025/09/25: OSD
CEN/TC 275 | DIN | 00275389 | 81469 | prEN 15634-7 | Foodstuffs - Detection of food allergens by molecular biological methods - Part 7: Peanut (Arachis hypogaea) - Qualitative detection of a specific DNA sequence in food by real-time PCR | Start of draft translation | 40.10.6001 | Homegrown | 10.99.0000 | 2025-02-20 | 2025-02-20 | 30.99.0979 | 2025-10-17 | 2025-10-17 | 40.20.0000 |  | 2026-01-22 | 40.60.0000 |  | 2026-04-16 | 45.99.0979 |  | 2026-12-03 | 50.20.0000 |  | 2027-02-11 | 50.60.0000 |  | 2027-04-08 | 60.55.0000 |  | 2027-05-06 | 60.60.0000 |  | 2027-06-03 | 2025-03-04: OSD
CEN/TC 158 | SIS | 00158121 | 81245 | CEN/TR 18249:2025 | Head protection - Scientific background and rationale to EN 17950 | Closure of Vote on TR | 50.60.0000 | Homegrown | 10.99.0000 | 2025-01-14 | 2025-01-14 | 30.99.0979 | 2025-07-08 | 2025-07-08 | [9 empty] | 50.20.0000 | 2025-08-14 | 2025-08-14 | 50.60.0000 | 2025-11-06 | 2025-11-06 | 60.55.0000 |  | 2025-12-07 | 60.60.0000 |  | 2025-12-17 | OSD 2025-07-02: Initial submission made on 2025-06-18. Due to a bug in CCMC systems, submission was reprocessed by CCMC on 2025-07-02.
CEN/TC 261 | AFNOR | 00261540 | 81852 |  | Packaging — Design for recycling — Part 2: Testing protocol for aluminium packaging | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-04-23 | 2025-04-23 | 30.99.0979 |  | 2025-12-29 | [9 empty] | 50.20.0000 |  | 2026-03-30 | 50.60.0000 |  | 2026-06-22 | 60.55.0000 |  | 2026-07-20 | 60.60.0000 |  | 2026-08-17 | 202/04/28:OSD
CEN/TC 162 | DIN | 00162510 | 81659 | prEN 469 rev | Protective clothing for firefighters - Performance requirements for protective clothing for firefighting activities | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-03-27 | 2025-03-27 | 30.99.0979 |  | 2025-10-28 | 40.20.0000 |  | 2026-01-27 | 40.60.0000 |  | 2026-04-21 | 45.99.0979 |  | 2027-01-07 | 50.20.0000 |  | 2027-03-18 | 50.60.0000 |  | 2027-05-13 | 60.55.0000 |  | 2027-06-10 | 60.60.0000 |  | 2027-07-08 | 2025-04-02: OSD
CEN/TC 107 | DS | 00107098 | 81137 |  | Development of energy system-integration | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-01 | 2025-10-01 | 30.99.0979 |  | 2026-10-31 | [9 empty] | 50.20.0000 |  | 2026-12-07 | 50.60.0000 |  | 2027-03-01 | 60.55.0000 |  | 2027-03-15 | 60.60.0000 |  | 2027-03-29 | 2025-10-13: OSD
CEN/TC 275 | DIN | 00275384 | 80388 | prEN 16802 rev | Foodstuffs - Determination of elements and their chemical species - Determination of arsenic species in foodstuffs by anion-exchange HPLC-ICP-MS | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-08-14 | 2025-08-14 | 30.99.0979 |  | 2026-04-09 | 40.20.0000 |  | 2026-07-09 | 40.60.0000 |  | 2026-10-01 | 45.99.0979 |  | 2027-05-27 | 50.20.0000 |  | 2027-08-05 | 50.60.0000 |  | 2027-09-30 | 60.55.0000 |  | 2027-10-28 | 60.60.0000 |  | 2027-11-25 | OSD
CEN/TC 182 | DIN | 00182101 | 77731 | prEN 14624 | Performance of portable locating leak detectors and of fixed gas detectors for all refrigerants | Submission to Enquiry | 40.20.0000 | Homegrown | 10.99.0000 | 2024-08-09 | 2024-08-09 | 30.99.0979 | 2025-07-08 | 2025-07-08 | 40.20.0000 | 2025-11-06 | 2025-11-06 | 40.60.0000 |  | 2026-01-29 | 45.99.0979 |  | 2026-05-22 | 50.20.0000 |  | 2026-07-31 | 50.60.0000 |  | 2026-09-25 | 60.55.0000 |  | 2026-10-23 | 60.60.0000 |  | 2026-11-20 | OSD
CEN/TC 143 | SNV | 00143107 | 82910 | prEN 12413 rev | Safety requirements for bonded abrasive products | Decision on WI Proposal | 10.99.0000 | Homegrown | 10.99.0000 | 2025-10-21 | 2025-10-21 | 30.99.0979 |  | 2026-06-16 | 40.20.0000 |  | 2026-09-15 | 40.60.0000 |  | 2026-12-08 | 45.99.0979 |  | 2027-08-03 | 50.20.0000 |  | 2027-10-12 | 50.60.0000 |  | 2027-12-07 | 60.55.0000 |  | 2028-01-04 | 60.60.0000 |  | 2028-02-01 | 2025-11-13: OSD